## Sheet1
Problems: | Time Estimates: | Estimated Start Dates | Actual Time Spent:
Use Case Diagram
Sequence Diagram for web and IOS | Extra-Small | May 8th | 1
Object Model | Small | May 8th | 1
Design the Applicaiton In Figma | Medium | May 8th | 1
Smart Contract | Large | May 9th | 2.4
Hardhat Created and Contract Added | Large | May 9th | 1
Git Repository for Project | Small | May 8th | 1
NextJS Conntect to Wallet | Small | May 13th | 3
NextJS Call Contract Function | Small | May 13th
Design and Implement SQL Database | Medium | May 14th | 1
Express get route | Medium | May 12th | 3
CSS in NextJS | Medium | May 14th | 2
Reuseable Component | Medium | May 14th
NextJS | Large | May 13th
Connection to Express Route | Medium | May 13th
IOS Fetch from Express Server | Medium | May 14th | 1
Commenting in Code | Large | May 15th
Folder Management | Small | May 8th? | ?
Reflection Paper on Project | Medium | May 15th | 1
Presentation Video | Small | May 15th | 1